## Feuil1
Moods Project Timeline
Task | Plan Date | Assigned Person | Notes
Introduction | 2017-01-19 | Whole team | Team choosed, discuss interests and ideas
Discuss Project | 2017-01-24 | Whole team | Discuss the choice of project and the possibility of completion
Choose Project | 2017-01-26 | Whole team | Moods Android App
Project Proposal | 2017-01-31 | Whole team | Project's features and used softwares
Install Softwares | 2017-02-02 | Whole team | Install and start getting familiar with Android Studio and GitHub
Familiarize with Softwares | 2017-02-07 | Whole team | Familiarize withb GitHub and Android Studio
Familiarize with Softwares | 2017-02-09 | Whole team | Do the Android Studio Online Lessons
Design | 2017-02-14 | Will | App Layout
UML diagrams & SQLite Database | 2017-02-16 | Amir | Understanding of SQLite and do the UML diagrams
Features & Algorithm | 2017-02-21 | Étienne | Define the final features and the math algorithm
Finish Proposal | 2017-02-23 | Whole team | Finish all other requirements for the proposal
Prepare presentation | Reading Week | Whole team | Using the final proposal, prepare an orl presentation
Oral Presentation | 2017-03-07 | Whole team | Summary of written report
Start app layout | 2017-03-09 | Étienne & Will | Design on Android Studio
Start database | 2017-03-14 | Amir | Start a database using Firebase
Finish main windows | 2017-03-16 | Étienne & Will | Finish login, register and home page on Android Studio
Start basic implementation | 2017-03-21 | Étienne & Will | Start the Java impementation on Android Studio
Database Login and Register | 2017-03-23 | Amir | Make sure login and register account works with Firebase
Continue working | 2017-03-28 | Whole team | Amir on Firebase and Étienne & Will on Android Studio
Continue working | 2017-03-30 | Whole team | Amir on Firebase and Étienne & Will on Android Studio
Continue database | 2017-04-04 | Amir | Working database on Firebase
Finish other windows | 2017-04-06 | Étienne & Will | Finish friendlist, search and notification page on Android Studio
Finish layout | 2017-04-11 | Étienne & Will | Finish all app pages layout using Android Studio
Continue implementation | 2017-04-13 | Étienne & Will | Implementation on Adroid Studio
Show progress to teacher | 2017-04-18 | Whole team | Show layout and how Firebase works
Finish database | 2017-04-20 | Amir | Finish database on Firebase
Finish database with app | 2017-04-25 | Amir | Implement Firebase with app
Finalize app | 2017-04-27 | Whole team | Combine all
Testing | 2017-04-02 | Whole team | Debug
Testing | 2017-04-04 | Whole team | Final testing
Final Version | 2017-04-09 | Whole team | Finished Final version of app
Presentation to teacher | 2017-04-11 | Whole team | Presentation of completed app
Finish last testing problems | 2017-04-20 | Whole team | Adjust problems encoutered at presentation to teacher
Start documentation | 2017-04-21 | Whole team | Do the final documentation
Finish documentation | 2017-04-22 | Whole team | Finish document and prepare for presentation
Final Presentation | 2017-04-23 | Whole team | inal presentation to teacher and whole class