## Feuil1
Moods Project Timeline
Task | Plan Date | Assigned Person | Notes
Introduction | 2017-01-19 | Whole team | Team choosed, discuss interests and ideas
Discuss Project | 2017-01-24 | Whole team | Discuss the choice of project and the possibility of completion
Choose Project | 2017-01-26 | Whole team | Moods Android App
Project Proposal | 2017-01-31 | Whole team | Project's features and used softwares
Install Softwares | 2017-02-02 | Whole team | Install and start getting familiar with Android Studio and GitHub
Familiarize with Softwares | 2017-02-07 | Whole team | Familiarize withb GitHub and Android Studio
Familiarize with Softwares | 2017-02-09 | Whole team | Do the Android Studio Online Lessons
Design | 2017-02-14 | Will | App Layout
UML diagrams & SQLite Database | 2017-02-16 | Amir | Understanding of SQLite and do the UML diagrams
Features & Algorithm | 2017-02-21 | Étienne | Define the final features and the math algorithm
Finish Proposal | 2017-02-23 | Whole team | Finish all other requirements for the proposal
Prepare presentation | Reading Week | Whole team | Using the final proposal, prepare an orl presentation
Oral Presentation | 2017-03-07 | Whole team | Summary of written report
Start app layout | 2017-03-09 | Étienne & Will | Design on Android Studio
Start database | 2017-03-14 | Amir | Database and Class implementation at the same time
Finish 7 of the 15 windows | 2017-03-16 | Étienne & Will | Finish half of layout on Android Studio
Continue working | 2017-03-21 | Whole team | Database and layout
Finish layout | 2017-03-23 | Étienne & Will | Finish all 15 windows on Android Studio
Start basic implementation | 2017-03-28 | Will | On Netbeans (use UML diagrams)
Start networking | 2017-03-30 | Étienne | Use computer at home
Finish database | 2017-04-04 | Amir | Working database
Start implement | 2017-04-06 | Étienne & Will | On Android Studio with the finished windows
Continue networking | 2017-04-11 | Amir & Étienne | Using Étienne's computer
Continue working | 2017-04-13 | Whole team | Will: Implementation
Continue working | 2017-04-18 | Whole team | Amir & Étienne: Networking
Finish implementation | 2017-04-20 | Étienne & Will | Finished
Finish networking | 2017-04-25 | Amir & Étienne | Working network
Finalize app | 2017-04-27 | Whole team | Combine all
Testing | 2017-05-02 | Whole team | Debug
Testing | 2017-04-04 | Whole team | Final testing
Final Version | 2017-04-09 | Whole team | Finished Final version of app
Final Presentation | 2017-04-11 | Whole team | Oral presentation of completed app